## RevisedPlannedSheet-PHASE1
Requirements |  | Actual Start Date | Plan End Date | plan Team Efforts (hour) | Actual Team Efforts (hour) | Assigned Work | Team |  |  |  |  | Percentage complete | Remark
[7 empty] | Arun | Sidharth | Bhavana | Priyanka | Harshad
Requirement Collection | Completed |  |  |  |  | Arun | 16 |  |  |  |  | 100%
Data Model Addition and stylesheet changes | Completed | 2019-09-05 | 2019-09-13 | 16 | 14 | Siddharth/Harshad |  | 6 |  |  | 8 | 100%
Test Development Environment Setup | Completed | 2019-09-12 | 2019-09-12 | 8 | 11 | Harsahd |  |  | 6 |  | 5 | 100%
Project Creation and Menu addition | Completed | 2019-09-16 | 2019-09-16 | 6 | 2 | Bhavana |  |  | 6
Unplanned teamcenter issue resolved | Completed | 2019-09-16 | 2019-09-17 | 8 | 24 | Harsahd/Bhavana/Priyanka |  | 4 | 10 | 8 | 8 | 100%
UI Designing on client system 1. FillCriteria UI. 2.Property UI 3.Display UI 4.Unit testing at progneur | Completed | 2019-09-16 | 2019-09-23 | 8 |  | Harsahd/Bhavana/Priyanka |  |  | 4 | 8 | 8 | 100%
Client approval for UI | Completed | 2019-09-20 | 2019-09-24 | [8 empty] | 100%
Fill criteria UI functionality : SO No and date filter input | Completed | 2019-09-19 | 2019-09-23 |  |  | Harshad |  |  |  |  | 8 | 100%
Property UI Values list creation | Completed | 2019-09-19 | 2019-09-23 |  |  | Priyanka |  |  |  | 8
Property UI funcationaliy: Right and left table value display | Completed | 2019-09-24 | 2019-09-24 |  |  | Priyanka |  |  |  | 4 |  | 100%
Property UI funcationaliy: Right/Left property traversing button functionality | Completed | 43732 | 43733 |  |  | Bhavana |  |  | 8 |  |  | 100%
Property UI funcationaliy: Up/Down property move functionality, With merging | Completed | 2019-09-20 | 2019-09-26 |  |  | Harshad+priyanka |  |  |  | 12 | 16 | 100%
Display report UI Funcationaliy: To display columns | Completed | 2019-10-26 | 2019-10-26 |  |  | Priyanka |  |  |  | 8 |  | 100%
Display report UI Funcationaliy: Display data on table a. TDPS TC data mdoel understanding and data traversing | Completed | 2019-09-27 | 2019-10-10 |  |  | Bhavana(start from 30)+Priyanka(2 days) |  |  | 4 |  |  | 100%
SO_search... Query cretaed for so revision search | Completed | 2019-09-20 | 2019-09-20 |  |  | Bhavana+Priyanka+Harshad+Siddharth |  | 1 | 4 | 4 | 4 | 100%
Display report UI Funcationaliy: Sorting functionality with merging | Completed | 2019-10-01 | 2019-10-03 |  |  | Priyanka | [5 empty] | 100%
ITK code functionality for TDPS data fetching | Completed | 2019-10-09 | 2019-10-15 |  |  | Bhavana |  |  | 8 |  |  | 100%
Display report UI Funcationaliy: Generate Excel report | Completed | 2019-09-27 | 2019-10-03 |  |  | Harshad | [5 empty] | 100%
Test cases are prepared for TDPS | Completed | 2019-10-22 | 2019-10-23 |  |  | Priyanka |  |  |  | 8 |  | 90%
ACL work for Export to excel button | Completed | 2019-10-04 | 2019-10-04 |  |  | Priyanka |  |  |  | 8 |  | 100%
Sorting issue is resolved for numeric and date swt table columns | Completed | 2019-10-30 | 2019-10-30 |  |  | Bhavana |  |  | 8 |  |  | 100%
BMIDE SOA Customization (for performance issue) | Completed | 2019-10-21 | 2019-10-31 |  |  | Bhavana |  |  | 8 | 5 |  | 95%
1.Resolved SOA data population issue(Marshlling error) and data is populated on swt table with good time performance | Completed | 2019-10-30 | 2019-10-31 |  |  | Bhavana |  |  | 12
1.Code refine and cleaning 2.Performance improvement | Completed | 2019-11-01 | 2019-11-01 |  |  | Bhavana+Siddharth+Priyanka |  |  | 9
1.Multiple machine numbers data value is added with comma separation(eg. mach1,mach2). 2.Property values are cross checked with SO(Whose all data is available) 2. Jar deploymentand value cross checking testing 3.Jar is deployed on test server it as well as on TDPS's new clients system. | Completed | 2019-11-04 | 2019-11-04 |  |  | Bhavana |  |  | 9
API issue for some SO items | Completed | 2019-11-05 | 2019-11-05 |  |  | Bhavana |  |  | 9:30
Unit testing and jar deployment,Client meetings | Completed | 2019-11-06 | 2019-11-06 |  |  | Bhavana |  |  | 8
Testing at TDPS client side | In progress | 2019-11-06 |  |  |  | Praveen & Sargent
1.Discussion and discussed modications implementation,Validation and Testings are going on | In progress
Multisorting Implementation using Group by(Pahase 2) | [5 empty] | Priyanka
[6 empty] | Total Hours: | 16 | 11 | 104.3958 | 73 | 57
Date | Reason | Resource | Buffer Hours |  | Total Hours from 9-9-19
09-Sep to 10 - Sep 2109 | Other work/TDPS delay | Harshad | 5
2019-09-10 | Other work/TDPS delay | Harshad | 6 |  | 68
2019-09-09 | PPAP/TDPS delay | Bhavana | 8 |  | 120.3958
2019-09-10 | PPAP/TDPS delay | Bhavana | 8
2019-09-24 | TDPS Remote conn issue | Bhavana | 1
2019-09-30 | TDPS Remote conn issue | Bhavana | 2
2019-10-15 | TDPS Remote conn issue | Bhavana | 3:30
Progneur Holidays

## MainPlanSheet (hidden)
Requirements |  | Actual Start Date | Actaul End Date | plan Team Efforts (hour) | Actual Team Efforts (hour) | Assigned Work | Team |  |  |  |  | Percentage complete | Remark
[7 empty] | Arun | Sidharth | Bhavana | Priyanka | Harshad
Requirement Collection | Completed |  |  |  |  | Arun | 16 |  |  |  |  | 100%
Data Model Addition and stylesheet changes | Completed | 2019-09-05 | 2019-09-12 | 16 | 14 | Siddharth/Harshad |  | 6 |  |  | 8 | 100%
Test Development Environment Setup | Completed | 2019-09-12 | 2019-09-12 | 8 | 11 | Harsahd |  |  | 6 |  | 5 | 100%
Unplanned teamcenter issue resolved | Completed | 2019-09-16 | 2019-09-17 | 8 | 24 | Harsahd/Bhavana/Priyanka |  | 4 | 10 | 10 | 10 | 100%
UI Designing on client system | In Progress | 2019-09-16 |  | 24 |  | Bhavana/Priyanka |  |  | 6 | 6 | 6 | 50%
Report Wizard Implementation with customer approval | Not Started |  |  | 32 |  | Bhavana/Priyanka
Filters | In Progress | 2019-09-11 |  | 32 | 16 | Bhavana/Priyanka |  |  | 8 |  | 8 | 60%
Logic Implementation to fetch Property values according to requirement | Not Started |  |  | 40 |  | Bhavana/Priyanka
Column management - preference value | Not Started |  |  | 40 |  | Bhavana/Priyanka
Dynamic Column Sorting using Nattable (Multi-Sorting) with Code merging with actual code and Testing | In Progress | 2019-09-03 |  | 160 | 62 | Bhavana+Priyanka |  |  | 6 | 56 |  | 80%
Access control | Not Started |  |  | 24 |  | Bhavana/Harsahd
Phase - 1 Code merging and Testing | Not Started |  |  | 64 |  | Bhavana + Harshad
Buffer (Phase 1) |  |  |  | 30
Filter- FERT From & To | Not Started |  |  | 48 |  | Bhavana/Harshad/Priyanka
Selected Report Column Saving for individual users | Not Started |  |  | 32 |  | Bhavana/Harshad/Priyanka
Phase -2 Code Merging and Testing | Not Started |  |  | 40 |  | Bhavana/Harshad/Priyanka
Buffer (Phase 2) |  |  |  | 30
Data model analysis and property mapping | Completed | 2019-09-12 | 2019-09-13 | 32 | 28 | Bhavana/Harshad/Priyanka |  |  | 4 | 16 | 8 | 100%
[6 empty] | Total Hours: | 16 | 10 | 40 | 88 | 45
Date | Buffer | Reason | Resource | Hours |  | Total Hours from 9-9-19
09-Sep to 10 - Sep 2109 |  | Other work/TDPS delay | Harshad | 5
2019-09-10 |  | Other work/TDPS delay | Harshad | 6 |  | 56
2019-09-09 |  | PPAP/TDPS delay | Bhavana | 8 |  | 56
2019-09-10 |  | PPAP/TDPS delay | Bhavana | 8

## InternalPlanSheet
Sr no | Date | Task | System | Start Date | End Date | Resource |  |  |  | Status | Working hours
[6 empty] | Bhavana | Priyanka | Harshad | Siddharth
1 | 2019-09-12 | Data model anlysis | Client | 2019-09-05 | 2019-09-12 | 6 | 8 | 8 |  | Completed | 22
2 | 2019-09-12 | Envirnoment setup | Client | 2019-09-12 | 2019-09-12 | 2 |  |  |  | Completed | 2
3 | 2019-09-13 | a. Menu creation and Fill criteria UI development on client machine b. Multisorting and bug fixing work on local system | Client/Local | 2019-09-13 | 2019-09-13 | 8 |  |  |  | Completed | 8
4 | 2019-09-13 | Data model analysis sheet display name real name property mamming documentation | Local | 2019-09-13 | 2019-09-16 |  | 16 | 16 |  | Completed | 32
5 | 2019-09-16 | a.Fill criteria UI modifications done on user system. B.Property display UI initial view displayed. | Client | 2019-09-16 | 2019-09-16 | 6 |  |  |  | Completed | 6
|  | b.Teamcenter login issue | Client | 2019-09-16 | 2019-09-17 | 10 | 8 | 8 | 3 | Completed | 29
| 2019-09-18 | Teamcetner preference is created on client system | Client | 2019-09-18 | 2019-09-18 |  | 4 |  |  | Completed | 4
|  | Fill criteria, property display and Report generation UI is ready on user sysstem | Client | 2019-09-18 | 2019-09-18 | 8 | 4 | 8 |  | Completed | 20
| 2019-09-19 | All UI's with are ready on Client system. Property UI right,left columns values are reflected using list on UI | Client | 2019-09-19 | 2019-09-19 | 8 |  |  |  | Completed | 8
|  | Excel Generation logic is ready | Local | 2019-09-19 | 2019-09-19 |  |  | 8 |  | Completed | 8
|  | For Property UI right,left columns values list get ready. | Local | 2019-09-19 | 2019-09-19 |  | 8 |  |  | Completed | 8
| 2019-09-20 | 1. All UI's get ready and demo given to Client | Client | 2019-09-20 | 2019-09-20 | 4
|  | SO_search... Query is generated in client system and data fetching code is in progress | Client | 2019-09-20 | 2019-09-20 | 4 | 4 | 4
|  | Up down functionality work is in progress | Local | 2019-09-20 | 2019-09-24 |  | 4 | 4
| 2019-09-23 | TDPS Data traversing logic implementation | client | 2019-09-23 | 2019-09-27 | 8 | 2 | 2
|  | Muli selection up down functionality work | local | 2019-09-23 | 2019-09-24 |  | 6 | 6
| 2019-09-24 | TDPS Data traversing logic implementation | client | 2019-09-24 | 2019-09-27 | 7
|  | Muli selection up down functionality work done | local | 2019-09-24 | 2019-09-24 | 1 | 8 | 8
| 2019-09-25 | TDPS Data traversing logic implementation | client | 2019-09-25 | 2019-09-27 | 8
|  | Group by nattable implementation | local | 2019-09-25 |  |  | 8 | 8
| 2019-09-26 | TDPS Data traversing logic implementation | client | 2019-09-26 | 2019-09-27 | 8
|  | a. Property file is created for TDPS property tables(Right,Left table) b.Group by nattable implementation | local | 2019-09-26 | 2019-09-26 |  |  | 8
|  | Property file reading logic is implementaed for TDPS property tables(Right,Left table) | local | 2019-09-26 | 2019-09-26 |  | 8
| 2019-09-27 | a. TDPS Data traversing logic implementation done b.property file code merging | client | 2019-09-27 | 2019-09-27 | 8
|  | Group by nattable implementation |  |  |  |  | 8 | Left TDPS
| 2019-09-30 | a.TDPS UI modifications and some data traversing related issues resolved. B.Prepared for demo | client | 2019-09-30 | 2019-09-30 | 8 | 8 | Left TDPS
|  | a.TDPS testing for demo b.Test cases are started to write | local | 2019-09-30 | 2019-09-30 |  |  | Left TDPS
| 2019-10-01 | Bug fixing and UI changes and Demo to user | client | 2019-10-01 | 2019-10-01 | 8 |  | Left TDPS
|  | Test cases is work in progess | local | 2019-10-01 |  |  | 8 | Left TDPS
| 2019-10-03 | a.Up down functionality work and Right left functionality enabled for user b.Functionality related work | Client | 2019-10-03 | 2019-10-03 | 8 |  | Left TDPS
|  | a.Test cases is work in progess b.Property file relaetd work | Local | 2019-10-03 | 2019-10-03 |  | 8 | Left TDPS
| 2019-10-04 | a.TDPS data fetching ITK code | Client | 2019-10-04 | 2019-10-04 | 8 |  | Left TDPS
|  | Export to excel button access control functionlaity | Local | 2019-10-04 | 2019-10-04 |  | 8
| 2019-10-07 | Some functionality testing with up/down other bug fixing | Local | 2019-10-07 | 2019-10-07 | 8 |  |  | Holiday working
| 2019-10-08 | Bug fixing and property values traversing issue fixing | Local | 2019-10-08 | 2019-10-08 | 8 |  |  | Holiday working
| 2019-10-11 | 1.Issue fixing and Bug fixing and property values traversing issue fixing 2.Excel report tesing and bug fixing | client | 2019-10-08 | 2019-10-08 |  | 8
| 2019-10-10 | Data traversing with ITK code | client | 2019-10-10 | 2019-10-11 | 8 | 8
| 2019-10-11 | 1.Data traversing with ITK code 2.Progress bar is added while data loading 3.Wrong input popup messages are created for date Priyankas code merging | client | 2019-10-11 | 2019-10-11 | 8
|  | 1.Excel sheet name is changed 2.Table Column header font changes are done 3.Popup messages conditions are validated | Local | 2019-10-11 | 2019-10-11 |  | 8
| 2019-10-14 | 1.Excel header coloring and formatting done 2.Popup messages for SO validation and date validations | Client | 2019-10-14 | 2019-10-14 | 8
|  | 1.SWT table columns header fortmating done 2.Functionality Testing | Local/Client | 2019-10-14 | 2019-10-14 |  | 8
| 2019-10-15 | 1.Property tables history is stored for same session of report UI 2.Started to write SOA service | Client | 2019-10-15 | 2019-10-15 | 4
|  | 1.Issue with BMIDE deployment 2.Property fetching and mismatc issue | Local/Client | 2019-10-15 | 2019-10-15 | 4 | 8
| 2019-10-16 | 1.Trying to resolve SOA service BMIDE deployment issue | client | 2019-10-16 | 2019-10-16 |  | 8
| 2019-10-17 | 1.Trying to resolve SOA service BMIDE deployment issue | client | 2019-10-17 | 2019-10-17 | 8 | 8
| 2019-10-18 | 1.SOA service is created succsessfully 2.Prepared system for demo | client | 2019-10-18 | 2019-10-18 | 8 | 8
| 2019-10-21 | 1.TDPS demo is done 2.Worked for small issues | client | 2019-10-21 | 2019-10-21 | 8 | 8
| 2019-10-22 | 1.TDPS SOA creation 2.TDPS column mismatch issue | client/Local | 2019-10-22 | 2019-10-22 | 8
| 2019-10-23 | Started to write TDPS Test cases | Client | 2019-10-22 | 2019-10-22 |  | 8
|  | Trying to resolveTDPS SOA build issue | client | 2019-10-23 | 2019-10-23 | 8 | 8
| 2019-10-24 | 1. SOA code build issue is resolved 2. Cold deployment for OA Ledger service is done 3. SO_search objects function code issue is resolved with multiple inputs. 4.Others unplanned issues are resolved. 5.BMIDE Deployed for SOA successfully | Client | 2019-10-24 | 2019-10-24 | 8
| 2019-10-25 | SOA call from java with request and response.(Input/Output arrangement) | Client | 2019-10-25 | 2019-10-25 | 8
| 2019-10-30 | 1.Sorting issue is resolved for numeric and date swt table columns a. Property OBJECCT_DATA_TYPE new key addition in code as well as property file b. Data type read in code 2.Populate SOA response values on SWT table | client | 2019-10-30 | 2019-10-30 | 13
| 2019-10-31 | 1.Resolved SOA data population issue(Marshlling error) and data is populated on swt table with good time performance | client | 2019-10-31 | 2019-10-31 | 12 | 6
| 2019-11-01 | 1.Code refine and cleaning 2.Performance improvement | client | 2019-11-01 | 2019-11-01 | 9
| 2019-11-04 | 1.Prepared for Demo 2.Resolve jar deployment issue but still jdk version issue is therefor SOA call | client | 2019-11-04 | 2019-11-04 | 9
| 2019-11-05 | 1.Multiple machine numbers data value is added with comma separation(eg. mach1,mach2). 2.Property values are cross checked with SO(Whose all data is available) 2. Jar deploymentand value cross checking testing 3.Jar is deployed on test server it as well as on TDPS's new clients system. | client | 2019-11-05 | 2019-11-05 | 10
| 2019-11-06 | 1.Bug fixing and latest jar deployment on user's machine 2. As discussed with Sargent and Praveen I have modified the below property lines(Highlighted in bold font : real name,object type,data type) from LeftColumnList.properties file. 1=TDPSSORevisionMaster:tdps_quantity:Quantity:integer old 1=TDPSSORevisionMaster:tdps_mac_qty:Quantity:integer new 42=TDPSSOEnggForm:tdps_design_categroy :Design Category:integer old 42=TDPSFERTRevisionMaster:tdp2_design_category:Design Category:string new 3.Meetings are done with Prasad,Praveen,Kiran and Sargent from TDPS 4.Report cross checking | client | 2019-11-06 | 2019-11-06 | 10
| 2019-11-07 | 1.Testing 2.Next button enable bug is fixed for without SO selection and Only date selection input criteria. | client | 2019-11-07 | 2019-11-07 | 9
| 2019-11-08 | 1. Wroking for code improvemnt. 2.Meetings are done with client | client | 2019-11-08 | 2019-11-08 | 9
| 2019-11-11 | 1.Working for TDPS functionality enhancement and testing | client | 2019-11-11 | 2019-11-11 | 8 | 4
| 2019-11-12 | 1.Worked for Filteria criteria cehcks on "Next" button | client | 2019-11-12 | 2019-11-12 | 8
| 2019-11-13 | 1.Working for TDPS functionality enhancement and testing | client | 2019-11-13 | 2019-11-13 | 8
| 2019-11-14 | 1.Working for TDPS functionality enhancement and testing | client | 2019-11-14 | 2019-11-14 | 8
| 2019-11-15 | 1.Working for TDPS functionality enhancement and testing | client | 2019-11-15 | 2019-11-15 | 8
| 2019-11-18 | 1.FERT id with Revision is added 2.TDPS testing 3.Jar is provied to user 4.Making notes of Phase2 SOW points | client/Local | 2019-11-18 | 2019-11-18 | 9 | 4
| 2019-11-19 | 1.Working for TDPS functionality enhancement and testing | client | 2019-11-19 | 2019-11-19 | 8
| 2019-11-20 | 1.Working for TDPS functionality enhancement and testing | client | 2019-11-20 | 2019-11-20 | 8
| 2019-11-21 | 1.Working for TDPS functionality enhancement and testing | client | 2019-11-21 | 2019-11-21 | 8
| 2019-11-22 | 1.RPA Automation anywhere study 2. "SO FROM" has SO- by default which means SO-* 3. "SO To" has set blank by default. 4. Next is enabled by default. (If all fields with blank input (without any input) then " Next" button will disable). 5. Unit of measurement: Left side property names are renamed 6. 4 decimal points have been added for below points. | client | 2019-11-22 | 2019-11-22 | 8
[5 empty] | Total: | 394 | 230 | 88 | 3

## Change Document for TDPS Req
| Sr. No. | SOW Requiremnt | Changed Requirement
| 1 | SO Number single searching | So Number Range Searching | done
| 2 | Normal Sorting | By default fixed sequence for right table properties & sorting sould bedone with only new properties
| 3 | No refresh button | Refreshs button should be there above up/down utton
2019-11-04 | 4 | Multiple Machine nos with comma seperated | If multiple Machine nos are available then it should be in next row one by one

## demo points
10-10-2019 -Demo Points
1 | UI color chnages with normal | happen once will get another client system |  | Demo
2 | UI column name should be bold | priyanka
3 | Excel name should be OA Ledger | bhavana | complete
4 | Excel column headers should be with background color and bold | priyanka | complete
5 | If the report for perticular SO will not be available then show popup message | bhavana | complete
6 | Wrong date selection popup message | bhavana | complete
7 | Same seession property selection history should be stored | bhavana | complete
8 | time performance | bhavana | complete
9 | Progress bar for work completion | bhavana | complete
| 2019-10-21 |  |  | Demo
1 | By default "SO-" string shold be set to both SO text box | bhavana | complete
2 | SO input validation check on next button for filter criteria UI | bhavana | complete
3 | Test Cases | Priyanka | complete
4 | Column mismatch issue | bhavana | complete
5 | Sorting issue | bhavana | complete
| 2019-11-04 |  |  | Demo
1 | If multiple Machine nos are available then it be comma seperated | bhavna | completed
2 | If multiple Machine nos are available then it should be in next row one by one | new chnage
3 | Test cases need to send | bhavana | completed
4 | Last minuites of meeting output and verification comments have to send to Prasad
2019-11-08
Today's meetings MOM as follows
1.The SO numbers which don't have FERT id displayed in report these are Spare type SO numbers
-> agreed
2. For spare type of SO numbers show bomid in FERT column.
3.SO Type drop down(With 4 values) want on search criteria( for separate Spare SO and FERT connected SO report).
3.If multiple machines are available for same SO, how TDPSMachineRevisionMaster's date properties can be managed in report.
4. Progneur's innovative messages for search criteria next button
eg. SO From : SO-11-0001
SO To : SO-11-0500
date from : 01-02-2019
date to :01-03-2019
Message:Should i terminate and go back to the input window, or change the date range and go by the rule.

## Phase-2 Points
Phase -1
Sr no | Task | Remark
1 | By default "SO-" is appearing in both From & To and Next is not enabled.
2 | Once user will enter inout next button will be enable.
2 | Single input for SO From/TO can be entered
3 | Inputs can be allowed SO-*,SO-12*,SO-12-*,SO-12-0X*,SO-12-00XX, so-*,so-12*,so-12-*,so-12-0X*,so-12-00XX in this criteria
4 | Instead of FERT -> FERT ID + Revision to appear
Phase-2
Sr no | Task | Remark
1 | Fert Filter From & To on UI and data fetching logic | posible
2 | User able to save selected columns | possible
3 | Spares SO | posible
4 | Very quick report fetch by saving SO data in separate database | possible
5 | SO From should be graer than SO To in serach criteria ,if not alert popup should display Message : Data is not availabe for given input search criteria. Please try with different inputs. eg. SO-01-0011 to SO-01-0015 SO-11* to SO-11-9999 SO-11* | Possible
6 | If small date range have more SO numbers(>=500) filter so display(Improper range ) message as below Message: You are trying to search maximum SO objects in low duration. Do you want to terminate and go back to the input window, or go ahead. | Possible
7 | Add Logic : If multiple Machine nos are available then it should be in next row one by one | IT is possible but time consuming
8 | Add Four New Fileds of TDPSMachineRevisionMaster (Delivery as per Contract,Commissioning Date,Internal Planned Date,Business Unit). | Possible but it is related with diff machine numbers which TDPS wants in new row May be it will make difficulty in sorting
9 | Properties should display on same position after travering from right to left vice versa. | It is complex and time consuming case for logic
10 | While sorting 13 properties of right side column should fix reaming properties should sort | Possible ,but time consuimng
11 | Refresh button : To restore the sorted data in previous sequence | Possible ,but time consuimng
12 | "SO Type" drop down wants on search criteria UI | Possible
13 | Add Logic : segregating the spare SO's and normal SO's accoring to SO Type | Possible
14 | Add Logic : BOM ID should be there for spare SO's in FERT column | Possible

## Sheet2
1. Selected columns for bmide data fetching
2.data type addition in property file | bhavana
3.Data type read in code | bhavana
4.numric sorting issue | bhavana